## Lucas
Project review report
Project: | SAP ATC-1st floor Hyderabad | [5 empty] | Consultant: |  | Niroop Associates
Client: | SISL |  |  | Budget: | 5.43' mio | RS. Mio | Final |  | RS. Mio | Consultancy | 0'5 | RS. Mio
Schedule | Start: 02.05. 2006 |  | Finish: 25.06.2006 |  | Date Ammendments: |  |  |  |  | Received |  | RS. Mio
Project leader / coordinator |  | Ms. Kalyani |  | Project team: |  | SRE - Ms. Kalyani + Mr. Vedant + Mr. Daftary
|  | Mr. Vedant Patel |  |  |  | SISL - Mr. Venkatesh
Project scope: |  | Refurbishing of 6,400 sqft of space on 1st floor for SISL.
Infrastructure includes A/C,UPS wring, LAN & tele wiring, furniture, carpeting, false ceiling, internal partitions, cafeteria,toilet refurbishing works,other civel works, internal finishes etc
Investments: |  | SISL: | 5.43' mio | RS. Mio | Client: |  | RS. Mio | Remarks
Project stage: |  | Approval | Project approved on 22-04-2006 |  |  |  | Planning | Drgs. Are in final stage of approval - by 26.05
|  | Execution | Ceiling demolition work is in progress |  |  |  | Completion | As per schedule.
Major Vendors list: |  | Work |  | LOI/PO Status | PO value | Processed | Paid | Work status / Remarks
M/s Niroop Associates |  | Interior work |  | LOI issued |  |  |  | Civil work in progress,Demolition of walls and toilet walls and stripping of pop ceiling in progress
Electrical works |  | Electrical works |  | LOI issued |  |  |  | PO to be issued
Networking job |  | Networking job |  | LOI issued
V3 engineers/Space 10 |  | Modular furniture |  | Negotiation stage |  |  |  | To be finalized by 29.05
Daiken/Voltas/Bluestar |  | Air conditioning |  | Negotiation stage |  |  |  | To be finalized by 30.05
Numeric/Emerson |  | UPS |  | Negotiation stage |  |  |  | To be finalized by 30.05
Godrej |  | Chairs |  | offer stage |  |  |  | To be finalized by 29.05
0
Cash out flow: Through SISL
| OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEPT
Planned | MAY: 2.2'mio; JUN: 2'mio; JUL: 1.03'mio
Actual
Decision awaited: | JUN: Action by; JUL: date; AUG: Remark
NIL
Constraints if any: | JUN: Action by; JUL: date; AUG: Remark
|  | Being a function building, working in office hrs is not permitted. However it is aligned with the | [6 empty] | SRE
vendor for execution in after office hrs.
Other information | JUN: Last & Next Site meetings:
[9 empty] | 16.05 | M/s Vedant & team
[9 empty] | 1.06 | M/s Vedant & team
Project progress status: | DEC: As of today project is running as per the schedule.; JUN: Ahead; JUL: On time; AUG: Behind; SEPT: time overrun
Initiated by / date | JAN: Updated by / date; MAY: Next update/ date
Vedant | JAN: Kalyani - 25.06; MAY: Kalyani - 24.06